REPORT OF COORDINATOR

term 1 2018/2019

school name	INSTITUTO DE EDUCACIÓN SECUNDARIA JOSÉ MARÍN (SPAIN)
coordinator	DIEGO GEA PÉREZ

number of teachers involved in project	DIEGO GEA, CRISTINA LIZARÁN, ESTHER CARRICONDO, LUCÍA SÁNCHEZ, ANTONIO MARTÍNEZ, LUIS MIGUEL, CRISTINA LÓPEZ, J.CARLOS RUBIO, LUCÍA CARRASCO.
number of students involved in project	Ramdat, Hannah Louise / Purchase, Nicole Denia / Navarro García, Leticia / Sánchez Asensio, María Beatriz / Sánchez Teruel, Luz María / Serrano Fernández, Claudia / Serrano Soriano, Natalia / Heredia Lázaro, Rafael / Pérez Teruel, Ana / Castillo Sánchez, Emma / Pérez López, David / María López González / Antonio Giner Reina / Paula López Ayén

### Project Event Details (according to mobility tool)
##### Please list and describe all project activities other international meeting for example: project management meetings, dissemination activities and other local activities and events in each school. The activities listed here will be included in the partnership final report as part of the project timetable.

Type of activity	start date	end date	short description
Project management	16/09/2018	10/10/2018	Selection of students participating in the erasmus project.
Project management	16/09/2019	15/10/2018	Geology topics have been included in the programming of the students participating in the project.
Dissemination activities	10/11/2018	30/11/2018	Design and presentation of 14 logos
Project management	01/12/2018	Actuality	Rock and fossil identification practices in the Biology and Geology laboratory
International mobility	04/11/2018	08/11/2018	Mobility to Cyprus. Geopark of Troodos. Previous study of the Ophiolites.
Diseemination activities	15/01/2019		Registration of 5 students in the regional Geology Olympiad.
Project management	15/11/2019	Actuality	Beginning of the preparation of the mobility to the geoparks of Spain of April 2019.